June 2024

# Review of the Children’s Disability Network Teams Service Model - Project Plan

Project timeframe: Approx. 1 year

# Contents

Executive summary	3

1. Introduction	4

2. Project aims and scope	6

Ethics	7

Review Aims	8

Research questions	8

External input	9

3. Methods:	10

Phase 1. Literature reviews	11

Phase 2.  A review of the operation of the Children’s Disability Network Teams	11

Phase 3. An evaluation of the experience of Primary Care and CAMHS staff in delivering children’s services	14

Phase 4. An evaluation of the experience of children and families in accessing CDNT services	14

Phase 5. Examination of the views of other stakeholders	17

Phase 6. Analysis of administrative data	17

Data protection	17

4. Project deliverables	17

Expected outcomes	17

Deliverables	17

5. Project timeframe	19

6. Summary of interviews	20

Appendix 1: Illustrative sample questions for CDNT teams	21

# Executive summary

The National Disability Authority (NDA) is the independent statutory body, providing evidence-based advice and research to Government on disability policy and practice and promoting Universal Design.

This document provides an outline of the NDA’s approach to reviewing the implementation of the Progressing Disability Services (PDS) programme to date. This is based on a request by the HSE and as outlined in the Roadmap for Service Improvement 2023-2026 which states

An Independent Review of the CDNT Service Model by the NDA will include a review of competencies and skill mix required and staffing to child population ratios across teams, to optimally support children and families. It will evaluate the experience of children and families in CDNT services, service providers and staff providing children’s disability services including CDNTs, Primary Care, CAMHS, and Disability Act Office.

The review is elaborated on further in action 2.17 in the Roadmap.

We intend to frame the review around the 12 principles of PDS. The review will be descriptive in nature and will focus on the experiences of parents of children with disabilities, children with disabilities as well as staff and managers. We propose to conduct a survey, interviews and focus group with parents, children, staff and management.

There will be some limitations in what the review can include and conclude. For example, it will not examine clinical practices and will not explicitly examine outcomes for children as those data are not readily available and would require a different design. It will not examine whether the existing national policy is the correct policy. The main focus will be on how the various teams and Regional Health Authorities (RHAs) are progressing towards providing a service that is line with national policy and the 12 principles of PDS. This will allow recommendations to be developed to strengthen PDS. However, although we are not reviewing whether the existing PDS policy approach is the most appropriate, if the review findings identify issues that may raise questions about the underlying policy, these will be explored and policy focused recommendations may be made.

We aim to have draft report to share with the HSE,DCEDIY and the Minister of State for Disabilities 12 months from the date that an MoU is signed.

# 1. Introduction

The Progressing Disability Services (PDS) programme began 12 years ago as part of Transforming Lives. The programme is based on the recommendations of a 2009 review of the provision of services to children with disabilities. Before the PDS model of service provision, disability services in Ireland developed in an ad hoc manner, leading to inconsistent services across the country. Under the PDS, children’s disability services are being reconfigured to ensure that services are provided in an equitable and consistent manner regardless of location, rendering them more in line with Ireland’s obligations under the United Nations Convention of the Rights of Persons with Disabilities.

As part of the reconfiguration under PDS, Children’s Disability Network Teams (CDNTs), consisting of health and social care professionals, have been established in each of the six RHAs within defined geographic areas aligned with Community Healthcare Networks. The CDNTs provide services and supports for all children aged from birth to 18 years living in the Network catchment area, who have complex needs as a result of their disabilities. There are 91 Children’s Disability Networks (CDNs) which align with 96 Community Healthcare Networks (CHNs).

The principles of PDS are the foundation for the type of service that CDNTs will provide. They were developed by the National Children’s Programme Oversight Group, based on evidence and consultation with staff and parents. The twelve principles are:

| - Accessibility | 7. Equity of Access |
| --- | --- |
| - Accountability | 8. Evaluation of outcomes |
| - Bio-psychosocial model | 9. Family centred practice |
| - Clinical governance & evidence based practice | 10. Inclusion |
| - Cultural competence | 11. Interdisciplinary team |
| - Early detection & referral | 12. Staff are valued and respected |

In the 12 years since the implementation of the PDS model was commenced, some areas have reconfigured quickly whereas other areas have been slower to reconfigure. As a result, some issues with implementation have been reported.

A review of CDNT services for Kildare and West Wicklow, conducted in 2016, identified a number of issues with the service including difficulties providing continuity of service because of high staff turnover and an inability to fill vacancies quickly, long waiting times for services, inequity in access to services once the child was accepted into CNDT service, a shortfall in administration resources and difficulties for teams working with other specialist services. The review also highlighted some positive aspects of the service however, for example, three quarters of families who completed the survey were happy with the physical access to local support services, and both staff and families valued the interdisciplinary approach.

More recently, a survey examining parents’ experiences of PDS, conducted by Inclusion Ireland in 2022, also identified a number of barriers to accessing services through PDS. The top three barriers were: a lack of services (reported by 83% of families), lack of communication (48% of families), and poor quality of services received (19% of families who had received services).

PDS has received some negative commentary in recent months, highlighting a lack of available resources and long waiting lists. It is likely, however, that in some areas, the services are working well for those who are receiving them. A formal independent review is, therefore, required to examine what is working well and what is not and to establish the extent to which the current operation of PDS is delivering a model of services in keeping with the 12 principles of PDS.  This will be the first in-depth formal nation-wide review of the PDS since its inception. The review will be descriptive in nature and will focus on the experiences of parents and children with disabilities as well as staff and managers with insights also provided by other stakeholders.

The ongoing issue of staff recruitment and retention is likely to have an impact on this review’s ability to fully assess whether PDS is delivering a model of services in keeping with the 12 principles. However, identifying which of the 12 principles are being fully implemented, even without a full compliment of staff, and identifying those that require more focus will provide useful information.

The issue of  is not fully encompassed within the 12 principles of PDS so this is an additional area that will be examined in the CDNM and CDNT questionnaires and interviews and as part of the literature review. The review will aim to identify leadership / management competencies that are required to support high performing interdisciplinary teams and whether these competencies are demonstrated among CDNMs. Good practice will be identified where possible,

# 2. Project aims and scope

The Roadmap for Service Improvement 2023-2026, Disability Services for Children and Young People. that has been developed to address the challenges facing PDS includes a review of the CDNT service. The broad scope of this review includes:

- A review of current literature regarding health and social care supports for children with disabilities

- Consideration of the competencies and skill mix required to support children with disabilities

- Review of the current allocation of staff resources to child population per team within a RHA

- A review of the operation of the Children’s Disability Network Teams with reference to the 12 principles of PDS

- An evaluation of the experience of children and families in accessing CDNT services

- An evaluation of the experience of service providers including CDNT, primary Care, CAMHS staff and Disability managers (PDS leads, national leads, therapy managers/ former heads of discipline) in delivering children’s services

- An assessment of the view and experiences of other stakeholders such as professional bodies, Disabled Persons Organisations, other disability groups including disability umbrella organisations and children’s organisations.

These broad parameters have been fleshed out by the NDA below into aims and research questions.

A review of whether the PDS model is the most appropriate model for Ireland is considered not to be in scope given how progressed implementation is and allowing for the need for any new system to have a period of embedding before being judged as being successful or not. The main focus will be on how the various teams and RHAs are progressing towards providing a service that is line with national policy and the 12 principles. However, the review will capture views on whether some elements of the model are not in line with best practice or are not functioning optimally and depending on the findings this may lead to some consideration of the current policy approach. Some areas that have been reconfigured for longer may provide some insight into the impact of the model but those are likely to be tentative findings. Examples of best or promising practices will be captured where relevant. This will all be conducted with a backdrop of challenges in recruitment and retention so a mix of CDNTs with various vacancy rates will be included.

Looking explicitly at outcomes for children with disabilities who access services through CDNTs is also out of scope. An examination of outcomes would require a more longitudinal study and would also require an examination of clinical practices which is not part of this review. It is important that this work is done at some point but will not be part of this review.  However, where information is obtained, for example through the literature review or surveys and interviews related to this topic we will consider whether there are ways that the service can be adapted to facilitate the future measurement of outcomes.

## Ethics

NDA will conduct this review in an ethical manner and will adhere to relevant safeguarding and data protection rules. We have previously published Ethical Guidance for research with adults with disabilities  and a report on Research with Children with Disabilities so are very familiar with ethical principles. As this is a review of an existing programme, formal ethical approval from a Research Ethics Committee is not deemed necessary. However, the NDA will anticipate, plan for, monitor and address ethical issues throughout the review process.  The reviewers will make it clear to participants that they can withdraw from a focus group or interview at any time and assent will be obtained from children to participate in the review.

## Review Aims

Specifically, this review will take a multi-method approach to:

Examine how other jurisdictions configure their services and determine the range and ratio of disciplines to child population required to deliver identified competencies to meet needs of children and their families'. This will be done in the context of the move to interdisciplinary working and will include a broad range of clinical and non-clinical competencies

Identify how other jurisdictions determine the optimum level of intervention for a child.

Review current allocation of staff resources to child population per RHA

Identify the competencies and skill mix required by professionals to adequately support children with disabilities

Identify what is working well within PDS

Identify what is working less well within PDS

## Research questions

How satisfied are parents with the quality of services their child has received, the family-centred approach and communications in relation to the services?

How satisfied are children with the services they have received?

How satisfied are parents , staff, and other stakeholders (such as umbrella disability organisations or children’s organisations) with the PDS structures and reconfiguration of services?

How satisfied are parents whose child is awaiting CDNT services

How satisfied are CDNT staff with the structures and processes within PDS including referrals, interdisciplinary working and the family-centred approach? What, if any, improvements do they suggest?

Is the operation of local Children’s Disability Network Teams in line with the model of service set out national policy documents (in particular with the 12 principles of PDS)?

Is there consistency in management and roll out of the programme across services?

Is the allocation of children to therapists/teams conducted in the same way across services?

- How is this calculated and how does this compare to how it is calculated in other jurisdictions and is there a best practice model?

- How is the level of supports/services a child receives calculated? How does this compare to other jurisdictions and is there a best practice model.

How well is the interface between CDNTs, CAMHS and Primary Care, working?

What are the trends in relation to waiting times for access to CDNT services?

## External input

### Consultative Committee

The Consultative Committee (CC) will be chaired by the Head of Policy, Research and Public Affairs from the NDA, representative(s) from the HSE, representative(s) from the Department of Children Equality Disability Integration and Youth (DCEDIY), a representative from the National Clinical Care Programme for People with Disability, and the NDA review team. An independent advisor may be appointed by the minister to join this group.

The purpose of this group is to:

- Provide advice and suggestions.

- Troubleshoot any difficult issues encountered.

- Review and provide feedback on a draft final report.

- Assist with dissemination of the report.

The NDA will retain full independence over the review and will take on board advice from the CC where relevant. This group will meet monthly initially and then as required.

### Review advisory group:

A Review Advisory Group (RAG) will be created that includes representatives of a range of stakeholders with an interest in the Progressing Disability Services policy such as:

- Disabled Persons Organisation

- Other disability organisations e.g. Inclusion Ireland, National Disability Services Association, Disability Federation of Ireland, Federation of Voluntary bodies

- Parent representatives e.g. from Family Representative Groups

- Other family groups e.g. Fuss

- A young adult who has direct experience of children’s disability services.

The role of the group is to

- provide advice and suggestions on the overall conduct and progress of the research.

- provide comment and advice on the research questions, methods, findings and outputs.

- exchange ideas and information relevant to the project.

The RAG will not receive a draft of the report. Rather the key findings and recommendations will be shared via presentation and their views sought and considered. This group will meet 4-6 times over the course of a year with additional meetings called as necessary.

### External stakeholders

NDA has met with HSE National Disabilities Operations and the  PDS Leads group to inform the design of our research instruments to ensure we are comprehensively capturing all aspects of the service. We may also consult with these staff again or some other key informants throughout the project such as academic experts or other relevant stakeholders.

## Independence

It is important to note that the NDA will retain independence in terms of writing the report, interpretation of results and deciding on the final content of the report.

# 3. Methods:

This review will use a combination of methods and are outlined as a number of different phases below:

Phase 1 – Literature Review

Phase 2 – A review of the operation of the Children’s Disability Network Teams

Phase 3 – An evaluation of the experience of Primary Care and CAMHS staff in delivering children’s services

Phase 4 – An evaluation of the experience of children and families in accessing CDNT services

Phase 5 – Examination of the views of other stakeholders

Phase 6 - Analysis of administrative data

## Phase 1. Literature reviews

### Literature review

A review of current literature will be conducted regarding health and social care supports for children with disabilities. Specifically, this review will examine:

how the caseload and workload for a therapist  in an interdisciplinary team is determined in other jurisdictions

how the level of services/supports a child receives is calculated in other jurisdictions

identify the non-clinical competencies and skill mix required by multi-disciplinary teams to adequately support children with disabilities and their families

examine the views of parents and children regarding the implementation of services in other jurisdictions including how these views are captured

- It should be noted that an initial review of the literature has shown that there are several gaps in evidence around some of the questions posed above.

## Phase 2.  A review of the operation of the Children’s Disability Network Teams

### Survey

- To review the operation of the children’s disability network teams, all CDNT team members and managers, including therapy managers / heads of discipline, across the country will be invited to complete online surveys. Surveys will ask the participants to identify which CDNT they work in, though answering won’t be compulsory.  This information will be used to combine survey, interview and focus group data in the 14 CDNTs sampled for analysis. Feedback on suitability and relevance of potential survey questions will be sought from HSE National Disabilities Operations, PDS leads and the advisory group members. A short pilot study will be conducted.

- The survey will consist of scales and free-text questions based on the 12 principles of the PDS self-audit tool. Questions will be developed that will create a useful base line for future follow-up surveys.

### Interviews and focus groups

A number of focus groups and one-to-one interviews will be held with service providers/professionals and managers, including CDNMs, therapy managers (former heads of discipline), involved in delivering CDNT services to evaluate the experience of service providers and staff.

- Two CDNTs from each of the six RHAs with an additional team from the two largest RHAs. Staff and the manager will be invited to interview and/or participate in focus groups. Teams will be purposely selected with the aim of obtaining representativeness across a number of criteria including:

Rural/urban areas

Length of time the team has been configured

Vacancy rates

A selection from HSE, section 38 and 39 teams

Size of waiting lists

- Participants:

CDNT members including administrative staff, clinical staff (e.g., psychologist, OT, SLT, Social Work, physio, Dietitian, nurse etc)(14 focus groups)

Children’s Disability Network Managers (CDNM) (14 interviews)

PDS leads and therapy managers/former heads of discipline (2 focus groups)

Senior managers (HSE, Lead Agencies, Partner Agencies) and national leads (4-5 interviews)

Dept. Children, Equality, Disability, Integration and Youth (PO and APO lead for PDS – 1 interview)

- Depending on availability of interviewees we may amend the interview schedule to facilitate their schedules. This may include doing some joint interviews with two or three people or conducting more or less focus groups.

#### Interview topics:

Interview and focus group questions will focus on the staff experiences of implementing PDS. Topic areas will include:

Staff satisfaction with the interdisciplinary team working processes within the programme

Staff satisfaction with the processes and structures within the programme (e.g., collaboration within and across services; managing referrals; support for staff; resourcing; training; family-centred practice).

Staff satisfaction with clinical supervision and clinical risk where relevant

Wait list management including how staff are allocated to children e.g. how are waiting lists and waiting timeframes managed in their team/network? Does the team have a protocol for waitlist management? Is the protocol adhered to?

Barriers to successful implementation of the programme and/or challenges faced by staff

Impact of resources assigned to Assessments of Need on delivery of services

Views on impact of delayed access to services on children

Workable suggestions for challenges or barriers raised and suggestions for improvement.

What is working well and capturing good practice in the form of case studies where relevant.

Views on the role of private therapists

- Questions for CDNMs, RHA, Lead and Partner Agency Senior disability management will include:

Policy approaches,

Recruitment and retention challenges etc.

Standard operating procedures

Impact of resources assigned to Assessments of Need on delivery of services

Classification of cases i.e. active and files not opened

Frequency and content of communications with parents

Risks related to long waiting lists

Questions for therapy managers/former heads of discipline will also focus on challenges in relation to clinical supervision.

### Analysis

- Data will be collected in the survey, interviews and focus groups on the relevant RHA and team. Cross tabulations may be used to categorise RHA and teams that are performing well or not so well regarding the 12 principles of PDS. No teams will be identified as part of the analysis.

Interviews and focus groups and free text sections of the survey will be summarised and analysed thematically.

## Phase 3. An evaluation of the experience of Primary Care and CAMHS staff in delivering children’s services

### Interviews and focus groups

1 focus group with Primary Care staff from across a number of RHAs

1 focus group with CAMHS staff from across a number of RHAs

National senior staff such as HSE Head of Ops for Primary Care and Head of Ops for Mental Health and CAMHS (three interviews) and Department of Health relevant leads.

### Interview topics

Interview and focus group questions will focus on the staff experiences of implementing PDS with a focus on referrals. Topic areas will include:

experiences of the referral processes – e.g., how are referrals to and from the CDNT services managed? What is working well/not so well? What are the main challenges? Is the existing Standard Operating Procedure working well?

experiences of communication and collaboration with CDNTs

satisfaction with the processes and structures involved in PDS in general including clinical supervision

identification of main challenges and proposed solutions

identification of things that are going well

### Analysis

- Interviews and focus groups will be summarised and analysed thematically.

## Phase 4. An evaluation of the experience of children and families in accessing CDNT services

### Parent/Guardian Surveys

To examine families’ experiences of accessing CDNT services online surveys will be conducted with:

Parents/guardians of children with disabilities who have received or are in receipt of CDNT services through the PDS programme.

If the child is old enough, there may be scope to include a section that they can complete from their own perspective.

Parents of children with disabilities who are waiting to receive CDNT services through the PDS programme.

The survey will include skip patterns so that questions will be tailored depending on whether the child is on a waiting list or in receipt of services. Survey topic areas will include:

how long they waited/are waiting for CDNT services

supports provided while on waiting lists

level of satisfaction with communication with/from CDNT

barriers to accessing services and proposed solutions

what services the child has received

the level of satisfaction with the quality of the services received

- These surveys will be distributed nationally through disability and parents’ groups. The surveys will ask the parents to identify which CDNT there child is seen by, though answering won’t be compulsory.  This information will be used to combine survey, interview and focus group data for the 14 CDNTs sampled for analysis. We anticipate a high response rate so will keep the questionnaire short and contained.

### Interviews/focus groups

A series of interviews and focus groups will be conducted with parents/guardians and children. Attempts will be made to include parents and children from across all six RHAs. The one-on-one interviews will allow some case studies to be developed and may be more accessible for children with disabilities who find it difficult to participate in a group.

10 one-on-one interviews and 3 focus groups of families of children with disabilities who have received CDNT services through PDS

10 one-on-one interviews and 2 focus group with children who have received CDNT services through PDS

5 one-on-one interviews and 1 focus group with families of children who have not yet received CDNT services through PDS but are on waiting lists

### Interview topics

- Interview and focus group topics are outlined below for each of the three categories.

#### Topics for parents/guardians with children receiving services

Topic areas for parents/guardians of children with disabilities who have received services will include

Families’ satisfaction with the processes and structures within PDS

Families’ experiences with CDNT waiting list

Families’ experiences of the referral processes

Families’ satisfaction with the quality of services received

Families’ experiences of being on waiting lists for CDNT services – e.g., communication, supports

Families’ experiences of individual family service plans – e.g. are they useful? And of follow-up?

Families’ perceived barriers to accessing their CDNT services

Use of private services

#### Topics for children

Topic areas for Children with disabilities who have received CDNT services through PDS will include:

Are they happy with the services they receive?

What are the good things about their CDNT services?

What are the not so good things about their CDNT services?

Are there any changes they would like to see?

#### Topics for parents/guardians without services

Topic areas for parents/guardians of children with disabilities who are on waiting lists but have not yet received any CNDT service through PDS will include:

What CDNT services are they on waiting lists for / what services do they expect to get from the CDNT?

How long have they been on the waiting list?

What has communication been like from the CNDT while on the waiting list?

Have they received any supports while on the waiting list (reference the supports they are supposed to receive outlined in the 2022 Policy Framework paper (p.25))

### Analysis

The survey of parents/guardians will be analysed descriptively. Cross tabulations by RHA will be performed. Any free text responses will be analysed thematically.

Interviews and focus groups will be summarised and thematically analysed.

## Phase 5. Examination of the views of other stakeholders

- Other stakeholders such as Disabled persons Organisations, disability advocacy groups and parents’ groups and professional bodies will be invited to make a written submission. These submissions will be analysed thematically. Some follow up interviews may be conducted where it is deemed that more information is required.

## Phase 6. Analysis of administrative data

- Data on trends in waiting lists for CDNT services will be analysed by RHA using data from the HSE’s performance reports. Discussions with the HSE national team may highlight other relevant data which may also be examined. Any data analysed will be anonymised in advance of transfer to the NDA.

## Data protection

Permission to record the interviews/focus groups will be requested for the purpose of summarising and analysis. A summary of the interviews/ focus groups will be written up within one month of the recording and the recordings will then be destroyed. Recordings will be stored in line with NDA’s internal policies. All transcripts will be pseudonymised and notes taken will be anonymised.

Personal information in the form of names, addresses and phone numbers will only be stored for the purposes of contacting participants. Once they have participated in a focus group/interview this information will be destroyed. However, if participants request a copy of the final report or to be informed of when it will be available their personal information will be kept for this purpose.

# 4. Project deliverables

## Expected outcomes

The findings from the surveys and interviews/focus groups will identify barriers to accessing CDNT services through PDS

The findings will also highlight what is working well within CDNTs

The findings will inform recommendations to improve CDNT services in line with the 12 principals of PDS

## Deliverables

An interim report based on a small number of well staffed teams

Draft final report with recommendations

Presentation to HSE and DCEDIY of key findings

Finalised report following HSE and DCEDIY correction of any errors relating to structures or processes. NDA will retain its independence as to what is included in the final report.

Alternative versions which may include child friendly version, Easy to Read version, Plain language summary etc.  These will be prepared after the main report has been finalised.

Depending on length, certain sections may be prepared as separate annex documents such as a detailed methodology including the questionnaires and interview question guides.  It is not anticipated that the recommendations will be prescriptive but rather highlight areas of concern and suggest approaches that may be taken to improve the CDNTs and associated services.

## Publication of Report

- The NDA will have to receive approval of the report from our Authority before publication. A draft report will be sent simultaneously to the HSE, DCEDIY and the Minster of State for Disabilities. Feedback will be considered, and the report amended as necessary. A final report will then be sent to the HSE, DCEDIY and the Minister. The HSE will have ownership of the final report and will choose a publication date in collaboration with the NDA

# 5. Project timeframe

| Task | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scoping |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advisory group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consultative Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Literature reviews |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Surveys |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development & Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interviews/focus groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development & Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HSE data sourcing and analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Written submissions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interim report write up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Report Write up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft report& presentation to HSE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Presentation to NDA Authority |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accessible documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# 6. Summary of interviews

| Phase | Interviewees | No. of interviews | No. of focus groups |
| --- | --- | --- | --- |
| Phase 2. A review of the establishment of the Children’s Disability Network Teams. | CDNT staff |  | 14 |
|  | CDNMs | 14 |  |
|  | DCEIDY representative | 1 |  |
|  | PDS leads Therapy managers / heads of discipline | 2 | 2 |
|  | Senior managers and national leads | 4 |  |
| Phase 3 Phase 3. An evaluation of the experience of primary Care and CAMHS staff in delivering children’s services | Service representatives from primary Care, CAMHS staff and Disability Act Office staff |  | 2 |
|  | HSE Mental Health Lead | 1 |  |
|  | HSE CAMHS Lead | 1 |  |
|  | HSE Primary Care Lead | 1 |  |
|  | DoH relevant leads | 2 |  |
| Phase 4. An evaluation of the experience of children and families in accessing CDNT services. | Parents of children with disabilities who have received CDNT services through the PDS programme | 10 | 3 |
|  | Children with disabilities who have received CDNT services through the PDS programme | 10 | 2 |
|  | Parents of children with disabilities who have not yet received any services through the PDS programme but are on waiting list for CNDT services | 5 | 1 |
| Total |  | 51 | 24 |

Roadmap for Service Improvement 2023 – 2026 (hse.ie)

HSE National Reference Group, 2009. Report of the National Reference Group on Multidisciplinary Disability Services for Children aged 5-18. Available from: https://www.hse.ie/eng/services/publications/disability/report%20of%20the%20national%20reference%20group%20on%20multidisciplinary%20disability%20services%20for%20children%20aged%205-18.pdf

Rush, D. 2016. Review of Kildare West Wicklow Network Disability Teams.

ibid

Inclusion Ireland, 2022. Progressing disability services for children and young people parent  experience survey report. Available at: https://inclusionireland.ie/wp-content/uploads/2022/03/Inclusion-Ireland-Progressing-Disability-Services-Report-March-2022.pdf

https://www.thejournal.ie/enable-ireland-complaint-5977792-Jan2023/; https://www.rte.ie/news/politics/2022/1201/1339418-politics-ireland/

Roadmap for Service Improvement 2023 – 2026 (hse.ie)

https://nda.ie/news/ethical-guidance-for-disability-research#:~:text=People%20with%20disabilities%20who%20don,capacity%20to%20provide%20explicit%20consent.

https://arc-w.nihr.ac.uk/Wordpress/wp-content/uploads/2020/02/Full-guidelines-for-Best-Practice-in-the-Ethics-and-Governance-of-Service-Evaluation-Final02.pdf

Includes health and social care professionals, nursing, , behavioural therapists, and other relevant professions.